## Performance in Initiating
Id | Research Ethics Committee Reference Number | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
| 14/SS/0049 | A Randomized, Double-Blind, Placebo-Controlled, Parallel-Group, 26-Week, Phase 3 Study of Two Doses of EVP-6124 or Placebo in Subjects with Mild to Moderate Alzheimer’s Disease Currently or Previously Receiving an Acetylcholinesterase Inhibitor Medication | 2015-07-15 | 2015-07-23 | No |  | 8 |  |  | No |  | Y | Y |  |  |  | Y |  |  |  | Suspended then closed by sponsor before any recruitment took place | Sponsor
| 15/EM/0014 | The BEADS Feasibility Pilot Trial | 2015-05-06 | 2015-05-20 | Yes | 16/07/2015 | 14 | 57 | 71 | No
| 15/YH/0051 | Smoking Cessation Intervention for Severe Mental Ill Health Trial (SCIMITAR): a definitive randomised evaluation of a bespoke smoking cessation service. | 2015-10-06 | 2015-10-12 | Yes | 10/11/2015 | 6 | 29 | 35 | Yes
| 13/LO/1595 | COgnitive behavioural therapy vs standardised medical care for adults with Dissociative non¬Epileptic Seizures: A multi¬centre randomised controlled trial (CODES). | 2014-12-04 | 2014-12-18 | Yes | 15/01/2015 | 14 | 28 | 42 | Yes
| 14/LO/0736 | Valuing Active Life in Dementia (VALID) Work Packages 3/4: a pilot trial and randomised controlled trial of Community Occupational Therapy in Dementia (COTiD­UK) | 2014-10-06 | 2014-10-10 | Yes | 12/11/2014 | 4 | 33 | 37 | Yes

## Sheet1
RECref | FullTitle | Date valid application received | Date NHS Permission Sent | RecruitmentDate | StartDate | Started | EndDate | Ended | SponsorOrg | ProjectID | Trust | Expr1000
14/SS/0049 | A Randomized, Double-Blind, Placebo-Controlled, Parallel-Group, 26-Week, Phase 3 Study of Two Doses of EVP-6124 or Placebo in Subjects with Mild to Moderate Alzheimer’s Disease Currently or Previously Receiving an Acetylcholinesterase Inhibitor Medication | 2015-07-15 | 2015-07-23 |  | 23/07/2015 | TRUE | 04/11/2015 | TRUE | EnVivo Pharmaceuticals Inc | 143780 | SHSC | SHSC
15/EM/0014 | The BEADS Feasibility Pilot Trial | 2015-05-06 | 2015-05-20 | 16/07/2015 | 16/07/2015 | TRUE | 30/11/2016 | FALSE | University of Nottingham | 165632 | SHSC | SHSC
15/YH/0051 | Smoking Cessation Intervention for Severe Mental Ill Health Trial (SCIMITAR): a definitive randomised evaluation of a bespoke smoking cessation service. | 2015-10-06 | 2015-10-12 | 10/11/2015 | 13/10/2015 | TRUE | 30/03/2018 | FALSE | University of York | 172273 | SHSC | SHSC
16/NW/0014 | Effects of Enhanced Home Treatment Care on the Speed of Recovery and Length of Inpatient Stay in Psychiatric Patients: A Randomised Controlled Pilot Trial | 2016-01-22 | 2016-01-28 | 01/02/2016 |  | FALSE |  | FALSE | Sheffield Health and Social Care | ZQ26 | SHSC | SHSC
15/SC/0714 | A Phase 3, double-blind, randomized study of RVT-101 versus placebo when added to existing stable donepezil treatment in subjects with mild to moderate Alzheimer's disease. | 2016-02-17 | 2016-02-17 |  |  | FALSE |  | FALSE | Axovant Sciences Ltd. | 192332 | SHSC | SHSC
13/LO/1595 | COgnitive behavioural therapy vs standardised medical care for adults with Dissociative non¬Epileptic Seizures: A multi¬centre randomised controlled trial (CODES). | 2014-12-04 | 2014-12-18 | 15/01/2015 | 18/12/2014 | TRUE | 31/07/2018 | FALSE | King's College London & South London and Maudsley NHS Foundation Trust | 136836 | SHSC | SHSC
14/LO/0736 | Valuing Active Life in Dementia (VALID) Work Packages 3/4: a pilot trial and randomised controlled trial of Community Occupational Therapy in Dementia (COTiD­UK) | 2014-10-06 | 2014-10-10 | 12/11/2014 | 12/11/2014 | TRUE | 30/12/2016 | FALSE | North East London NHS Foundation Trust | 152356 | SHSC | SHSC